## Log
Date Identified | What | Priority | Who | Due When | Status | Status Notes
2019-12-04 | Repair guarding on fan assembly 216 | High | C. Smith | 2020-02-13 | Initial
2020-01-23 | Update SOP 426.78.113 | High | R. Jones | 2020-01-24 | Complete | Completed 1/24/20
2020-02-20 | Example 1 | High | G. Moore | 2020-02-27 | In Progress | Parts arriving 3/15
2020-02-21 | Example 2 | Medium | A. Hammond | 2020-04-21 | Reviewed | WO Created
2020-02-22 | Example 3 | Low | A. Priester | 2020-06-21 | In Progress | Fabrication scheduled 4/16
2020-02-23 | Example 4 | High | C. Smith | 2020-07-15 | In Progress | Painting scheduled 5/17
2020-02-23 | Example 5 | High | T. Lavoe | 2020-07-29 | In Progress | Estop installation scheduled 7/10
2020-02-24 | Example 6 | High | A. Thomas | 2020-03-15 | Complete | Completed 2/25/20

## Dropdowns
High | Initial
Medium | Reviewed
Low | In Progress
Complete
Removed